## Draft effort and Time line
Preliminary Effort Estimation & Timeline for additional Microsoft D365FO Thai localized.
No. | Topic | Estimated Effort (MD) | Estimated Timeline | 2.1 Design(MD) | 2.2 Development(MD) | 2.3 Unit Test(MD) | 2.4 Test and prepare document (MD)
1 | Additional Reverse Unrealized VAT Add new fields and functions to support Reverse Unrealized VAT, and include the additional information in the tax reports. > Tax registration Number > Tax Address Type > Branch Number > Vendor account > Posting date | 12 | 2 Weeks | 2 | 5 | 2 | 3
2 | Withholding Tax Accounts Receivable Journal Report (Thailand) Modify the Microsoft Thailand Localization (MS TH Localization) for Accounts Receivable Withholding Tax to ensure the report functions correctly. | 6 | 1 Weeks | 2 | 1 | 1 | 2
3 | DMF for Journal Enhance the Data Management Framework (DMF) journal entities to support importing Tax Information. - Invoice number / Invoice date / Invoice receipt date - Tax invoice number / Tax invoice date / Tax invoice receipt date - Vendor account /Name /Tax branch / Tax ID/ Vendor address type | 9 | 2 Weeks | 1 | 5 | 1 | 2
4 | Combine Related Voucher with Main Voucher Customize the system to combine related vouchers into the main voucher, following the standard voucher grouping logic.Such as: > Reverse unrealized VAT (only auto reverse) > WHT tac transaction > Realized Exchange rate Gain loss > Etc. | 17 | 3 Weeks | 2 | 10 | 2 | 3
5 | Add Exchange Rate for Free Text Invoice Adjustment Add an Exchange Rate field to the Free Text Invoice screen and customize the system to use this field can Fixed rate instead of the standard exchange rate during processing. | 6 | 1 Weeks | 1 | 3 | 1 | 1
6 | Sales Order Line Inquiry – Order, Packing Slip, Invoice, and Remaining Quantity Develop a new inquiry screen to display the following quantity information for Sales Order lines: - Ordered Quantity - Packing Slip Quantity and Remaining Quantity - Invoice Quantity and Remaining Quantity | 10 | 2 Weeks | 2 | 3 | 1 | 4
7 | Purchase Order Line Inquiry – Order, Product Receipt, Invoice, and Remaining Quantity Develop a new inquiry screen to display the following quantity information for Purchase Order lines: - Ordered Quantity - Product Receipt Quantity and Remaining Quantity - Invoice Quantity and Remaining Quantity | 10 | 2 Weeks | 2 | 3 | 1 | 4
8 | Receipt / Tax Invoice Customize the Receipt/Tax Invoice functionality and Document to support the following formats: - Detail/ Summary - Before / After receipt | 23 | 4 Weeks | 5 | 10 | 3 | 5
9 | Bank Advance Modify the import logic so that the system no longer requires the Route Number, allowing bank statements to be imported according to the supported file format. | 5 | 1 Weeks | 1 | 1 | 1 | 2
10 | Currency Selling / Buying Exchange Rate Enhance the exchange rate functionality to: - Maintain separate Selling and Buying exchange rates. - Provide filtering options to display only Selling or Buying exchange rates. | 10 | 2 Weeks | 3 | 3 | 1 | 3
11 | Print Non-Posted Voucher for PO/SO Enable users to print Non-Posted Vouchers before posting Purchase Order or Sales Order invoices. | 7 | 1 Weeks | 2 | POC | POC | 5
12 | Split Fixed Asset by Quantity Enhance the Fixed Asset functionality to allow assets to be split based on quantity. | 11 | 2 Weeks | 1 | 8 | 1 | 1 | POC TC
13 | Number Sequence Group for Return Order Customize the system so that the appropriate Number Sequence Group is automatically assigned based on the selected Return Order configuration. | 5 | 1 Weeks | 1 | 2 | 1 | 1
14 | Print Multiple Vouchers Develop a function that allows users to print multiple vouchers simultaneously by specifying voucher numbers or batch numbers as selection criteria. Or select mutiple voucher for print in each time. | 19 | 3 Weeks | 2 | 12 | 3 | 2
15 | Picking List Display Sales Unit Customize the Picking List report to display both the Sales Quantity and the Sales Unit. | 7 | 1 Weeks | 1 | 2 | 1 | 3
16 | Separate Movement Journal for Issue and Receipt Customize Inventory Movement journal to: - Maintain separate Movement Journal setups for Issue and Receipt transactions. - Automatically assign a negative quantity when processing Issue transactions. | 6 | 1 Weeks | 1 | 3 | 1 | 1
17 | Restore Voided Sales Orders / Purchase Orders Develop a function to restore voided Sales Orders (SO) and Purchase Orders (PO) so they can be processed again. | 5 | 1 Weeks | 1 | 2 | 1 | 1 | POC TC
168
***Remark
Below is the Preliminary Effort Estimation & Timeline, consisting of the following phases:
1. Design – Functional-level design documentation only (does not include detailed type or field-level specifications).
2. Development
3. Unit Testing
4. Testing and Documentation Preparation
Recommended Project Phases
Phase 1
Additional Reverse Unrealized VAT
AR Withholding Tax Journal Report (TH)
DMF for Journal (Import Tax Information)
Total = 4 weeks
Phase 2
Combine Related Voucher
Add Exchange Rate for Free Text Invoice
Inquiry SO Line (Order/Packing/Invoice Qty)
Inquiry PO Line (Order/Receipt/Invoice Qty)
Receipt / Tax Invoice
Bank Advance
Currency Selling / Buying
Non-Post Voucher for PO/SO
Total = 8-12 Weeks
Phase 3
Split Fixed Asset by Quantity
Number Sequence Group for Return Order
Print Multiple Voucher
Picking List Display Sale Unit
Separate Movement Journal between Issue & Receive
Restore Void SO/PO
Total = 6-7 Weeks